## Contract Forecasting
Phase | Name | A: Current Cost Budget | B: Spent/Committed (Less Adv SCOs) | C: Spent/Committed Total | Current Period Cost | D: Unposted Internal PCI Cost | E: Unposted External PCI Cost | F: Unposted PCI Cost Adjusted | G: Cost to Complete | H: CTC Unposted PCIs | I: Cost Forecast | J: Revenue Budget | K: Unposted PCI Revenue | L: Unposted PCI Revenue Adjusted | M: Revenue Forecast | N: Projected Gain/Loss
102800 | Toilet Accessories | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 5750 | 0 | 0 | 5750 | 750
104413 | Fire Extinguisher Cabinets | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 5750 | 0 | 0 | 5750 | 750
TOTALS |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 11500 | 0 | 0 | 11500 | 1500